## COMMUNITY AND SOCIAL SERVICES
2013/2014 QUARTERLY REPORTING TEMPLATE:COMMUNITY SERVICES (SDBIP) PERFORMANCE INDICATORS AND TARGETS
strategy | Indicator | Baseline | Annual Target | Budget | Responsible Dept. | QUARTERLY PROJECTIONS | [7 empty] | Mid-year target achieved or not | Explanation of variance | Expenditure (amount spend | Internal Audit verified or not | Mitigation
[6 empty] | 1ST QUARTER |  | 2nd QUARTER |  | 3rd QUARTER |  | 4th QUARTER
[6 empty] | Projections | Actual | Projections | Actual | Projections | Actual | Projections | Actual
KPA .2. BASIC SERVICES AND INFRASTRUCTURE DEVELOPEMNT:
Provide sustainable Waste Management Programmes | No. of Households provided with waste collection services in Makweng, Matome, Mathibela and Rakgoatha | 7870 | 3370 | 1529750 | Comm Serv | 3370 | 3370 | 3370 | 3370 | 1 | - | 1 | - | 3370 | Waste was not collected according to the roaster due to continous breaking down of trucks |  | Exception Found First Quarter Through inspection of the quarterly report we noted that the target was not archived due to delay in the procurement of refuse bags and recruitment of beneficiaries. Second Quarter Although waste was collected but it was not according roaster due to continous breaking down of trucks. We determined that during December 2013 Waste was not collected for two weeks due to unavailability of trucks, further more community members were not informed that waste will not be collected. | Repairs of truck as and when they breakdown. Procurement of two new trucks during budget adjustments
[10 empty] | 3370 | - | 3370 | -
| No. of Households provided with waste collection services in Lebowakgomo | 8337 | 8337 | 300000 | Comm Serv | 8337 | 8337 | 8337 | 8337 | 8337 | - | 8337 | - | 8337 | Waste was not collected according to the roaster due to continous breaking down of trucks |  | Exception Found First Quarter We could not verify the correctness and accuracy of the information reported in the first quarter as the supporting documents were not submitted for audit purpose. Second Quarter Although waste was collected but it was not according roaster due to continous breaking down of trucks. We determined that during December 2013 Waste was not collected for two weeks due to unavailability of trucks, further more community members were not informed that waste will not be collected. | repairs of truck as and when they breakdown. Procurement of two new trucks during budget adjustments
| No. of businesses provided with waste collection services in Lebowakgomo | 100 | 100 |  | Comm Serv | 100 | 100 | 100 | 100 | 100 | - | 100 | - | 100 | Waste was not collected according to the roaster due to continous breaking down of trucks |  | Exception Found First Quarter We could not verify the correctness and accuracy of the information reported in the first quarter as the supporting documents were not submitted for audit purpose. Second Quarter Although waste was collected but it was not according roaster due to continous breaking down of trucks. We determined that during December 2013 Waste was not collected for two weeks due to unavailability of trucks, further more Businesses were not informed that waste will not be collected. | repairs of truck as and when they breakdown. Procurement of two new trucks during budget adjustments
| No. of institutions provided with waste collection services in Lebowakgomo | 70 | 70 |  | Comm Serv | 70 | 70 | 70 | 70 | 70 | - | 70 | - | 70 | repairs of truck as and when they breakdown. Procurement of two new trucks during budget adjustments |  | Exception Found First Quarter Through inspection of the quarterly report we noted that the target was not archived due to delay in the procurement of refuse bags and recruitment of beneficiaries. Second Quarter Although waste was collected but it was not according roaster due to continous breaking down of trucks. We determined that during December 2013 Waste was not collected for two weeks due to unavailability of trucks, further more Institutions were not informed that waste will not be collected. | repairs of truck as and when they breakdown. Procurement of two new trucks during budget adjustments
Waste disposal Management | Number of landfill compliance reports produced | 0 | 12 | 3006667 | Comm Serv | 3 | 0 | 3 | 2 | 4500 | - | 4500 | - | 2 | The site operation started in the last week of October and waste was received from November |  | Exception Found First Quarter Target was not archived due to landfill site being incomplete in the first quarter. However it came to our attention that the landfill site was officially opened on 08 November 2013 Second Quarter We determined that two report was compiled, it came to our attention that the operation of landfil site started in the last week of October 2013. Although the landfil site is operating we have observed that there are illegal dumpings e.g. Zone F Main Street and Zone B . | Ensure monthly audit and reporting
Waste minimization | No. of recycling forum meetings held | 2 | 4 | 50000 | Comm Serv | 1 | 1 | 1 | 1 | 3 | - | 3 | - | 2 | None |  | No Exception Found. | None
Community and Social Infrastructure Assets management and maintenance | No. of public facilities maintained and reports compiled | 1 | 4 | 50000 | Comm Serv | 1 | 2 | 1 | 17 | - | - | 1 | - | 19 | None |  | No Exception Found. | None
Coordination of advisory form | No. of disaster management advisory forum meetings held | 4 | 4 | 50000 | Comm Serv | 1 | 1 | 1 | 1 | 1 | - | 1 | - | 2 | None |  | No Exception Found. | None
Provide free basic services | Reviewed and Approved Indigent Register | 5000 | 1 | Opex | Comm Serv | 0 | 0 | 0 | 74 Indigent forms received and captured | - | - | 1 | - | 74 | The indicator is projected for fourth quarter target |  | No Exception Found. | None
Law enforcement on traffic legislation | No. of law enforcement road blocks conducted | 60 | 60 | Opex | Comm Serv | 15 | 18 | 15 | 16 | 1 | - | 1 | - | 34 | None |  | No Exception Found. | None
| No. of traffic fines issued | 3700 | 4000 | Opex | Comm Serv | 1000 | 3328 | 1000 | 3010 | - | - | 1 | - | 6338 | None |  | No Exception Found. | None
Impoundment of stray animals | No. of stray animals impounded |  | 50 | Opex | Comm Serv | 11 | 0 | 13 | 0 | 1 | - | - | - | 0 | Delay in the appointment of service provider to deliver animal bales |  | Exception Found. Target was not achieved in the first and second quarter. It came to our attention that the target was not achieved due to unavailability of annimal bales. There are some delays in the appointment of service provider | To appoint a term contractor for the delivery of animal bales
By-laws enforcement on street trading | No. of by-laws enforcement operations conducted | 12 | 12 | Opex | Comm Serv | 3 | 3 | 3 | 3 | 1 | - | 1 | - | 6 | None |  | No Exception Found. | None
| One internal committee on informal traders Established (joint responsibility between community,communications and LED) |  | 1 | Opex | Comm Serv | 1 | 1 |  | ¯ | 3 | - | 3 | - | 1 | None |  | No Exception Found. | None
Ensure compliance to traffic legislation by driving schools | No. of inspections conducted at driving school business premises |  | 2 | Opex | Comm Serv | 1 | 1 | 0 | 0 | 1 | - | 1 | - | 1 | None |  | No Exception Found. | None
| No. of driving schools registered on the database |  | 1 | Opex | Comm Serv |  |  | 1 | 1 | 13 | - | 13 | - | 1 | None |  | No Exception Found. | None
| No. of meetings held with the local driving school association |  | 4 | Opex | Comm Serv | 1 | 1 | 1 | 1 | 15 | - | 15 | - | 2 | None |  | No Exception Found. | None
Compliance to testing standards and prescribed legislation | No. of regular compliance audits conducted |  | 4 | Opex | Comm Serv | 1 | 0 | 1 | 1 | 1000 | - | 1000 | - | 1 | No audit was conducted by the DoRT |  | Exception Found. Target was not achieved in the first quarter as Department of Roads and Transport did not conduct inspections during the quarter under review.
| No. of inspectorate reports responded to within thirty (30) days | 4 | 4 | Opex | Comm Serv | 1 | 0 | 1 | 4 | 1 | - | - | - | 4 | None |  | No Exception Found. | None
Quality testing of driving licenses and vehicles | No.of learner driver tested | 4400 | 3200 | Opex | Comm Serv | 800 | 1081 | 800 | 906 | 3 | - | 3 | - | 1987 | None |  | No Exception Found. | None
| No. of applicants tested for learners license | 1400 | 1600 | Opex | Comm Serv | 400 | 702 | 400 | 469 | - | - | - | - | 1171 | None |  | No Exception Found. | None
| No. of professional driving permits issued | 840 | 840 | Opex | Comm Serv | 210 | 169 | 210 | 217 | - | - | 1 | - | 386 | Few clients applied for professional permits |  | Exception found. It came to our attention that target was not achieved in the first quarter due to theft of TELKOM cable which caused LSU to fail to capture fingerprints records | The department to make people aware of the services they render.
| No. of vehicles tested | 200 | 320 | Opex | Comm Serv | 80 | 350 | 80 | 235 | - | - | - | - | 585 | None |  | No Exception Found. | None
Registration and licensing of vehicles | No. of vehicles registered | 1200 | 1400 | Opex | Comm Serv | 350 | 537 | 350 | 538 | 1 | - | 1 | - | 1075 | None |  | No Exception Found. | None
| No. of vehicles licensed | 8400 | 8400 | Opex | Comm Serv | 2100 | 2753 | 2100 | 2422 | 1 | - | 1 | - | 5175 | None |  | No Exception Found. | None
Educate schools on public road safety | No. of education sessions conducted to schools |  | 12 | Opex | Comm Serv | 3 | 12 | 3 | 4 | 800 | - | 800 | - | 16 | None |  | No Exception Found. | None
Educate Livestock farmers about road safety | No. of education sessions conducted to livestock farmers |  | 4 | Opex | Comm Serv | 1 | 2 | 1 | 2 | 400 | - | 400 | - | 4 | None |  | No Exception Found. | None
Education and Awareness | No. of environemntal awareness campaigns conducted |  | 4 | Opex | Comm Serv | 1 | 0 | 1 | 0 | 210 | - | 210 | - | 0 | Delay in the delivery of awareness campaign equipment and material. Lack of Municipal Sound system. |  | Exception Found. It came to our attention that the target was not achieved due to delay in delivery of equipments and materials for awareness campaign. We determined that purchase requisition was submitted to SCM on the 3rd of December 2013 and the order was issued on 18 December 2012.
Optimize infrastructure investment through maintenance services | No. of taxi ranks maintained |  | 7 | Opex | Comm Serv | 1 | 2 | 2 | 5 | 50 | - | 50 | - | 7 | None |  | Exception Found Through inspection of the maintanance report and a confirmation from Facility Clerk we determined that 3 taxi ranks not 5 as reported, namely Seleteng, Mamaolo and Leporogong were maintained in November 2013. | None
| One public Library maintained at Lebowakgomo |  | 1 | Opex | Comm Serv | 0 | 0 | 0 | 1 | 1 | - | 1 | - | 1 | None |  | No Exception Found. | None
Create awareness on library services | No. of library awareness campaigns programme conducted |  | 4 | Opex | Comm Serv | 1 | 0 | 1 | 0 | 350 | - | 350 | - | 0 | Delay in the delivery of awareness campaign equipment and material. Lack of Municipal Sound system. |  | Exception Found. It came to our attention that the target was not achieved due to delay in delivery of equipments and materials for awareness campaign. We determined that purchase requisition was submitted to SCM on the 3rd of December 2013 and the order was issued on 18 December 2012. | Community Service Department to liase with the communication office when planning to conduct their awarnesses
Creation of EPWP work | No. of work opportunity created | 120 | 200 | 1198000 | Comm Serv |  |  | 200 | 200 | 2100 | - | 2100 | - | 200 | None |  | Exception Found. Through inspection of the report from Intergrated Reporting System used for recording EPWP Beneficiaries we determined that 199 beneficiaries were appointed during second quarter. | None

## FINANCE DEPARTMENT
2013/2014 QUARTERLY REPORTING TEMPLATE: FINANCE DEPARTMENT (SDBIP) PERFORMANCE INDICATORS AND TARGETS
strategy | Indicator | Baseline | Annual Target | Budget | Responsible Dept. | QUARTERLY PROJECTIONS | [7 empty] | Mid-year Targets Achieved or not | Explanation of variance | Expenditure (Amount Spend) | Internal Audit verified or not | Mitigation
[6 empty] | 1ST QUARTER |  | 2nd QUARTER |  | 3rd QUARTER |  | 4th QUARTER
[6 empty] | Projections | Actual | Projections | Actual | Projections | Actual | Projections | Actual
Monitor performance on budget. | Number of monthly budget reports compiled and forwarded to heads of departments | 12 | 12 | - | BTO | 3 | 3 | 3 | 3 | 3 | - | 3 | - | Six reports were compiled and forwarded to heads of departments | Trial Balance is sent to all Executive Managers and managers on monthly basis |  | Exception found We could not be provided with evidence to substantiate that the monthly budget reports were submitted to the Heads of Departments in the first quarter. | None
Ensure timeous financial reporting | Number of monthly budget performance reports compiled and submitted to stakeholders by the tenth of each month. | 12 | 12 | - | BTO | 3 | 3 | 3 | 3 | 3 | - | 3 | - | six monthly budget reprts were compiled. | Section 71 reports are sent to various Stakeholders on monthly basis |  | No Exception Found. | None
To pay creditors within thirty days upon receipt of invoices. | Percentage of creditors paid within thirty days | 100% | 100% | - | BTO | 100% | 91,95% | 100% | 87.49% | Target not achieved October 91.57% November-84.68% December 86.21% | Delay in submission of invoices | Invoices will be returned to respective suppliers if they are received late to change date of invoice. | 87.49% | Target not achieved October 91.57% November-84.68% December 86.21% | Delay in submission of invoices |  | Exception Found Target was not archived, it came to our attention that the cause non -payment of service providers within 30 days is late submission of invoices by the Service providers. | Invoices will be returned to respective suppliers if they are received late to change date of invoice.
To review suppliers database on a quarterly basis. | Municipal data base reviewed quarterly | 4 | 4 | - | BTO | 1 | 1 | 1 | 0 | Not Achieved | Service provider(Predicate Solutions) was appointed to install a database software in May 2013. The service provider was handed to ICT for the implementation, up to now the software isnt installed due to poor/unavailble ICT resources. As a result database forms couldnt be captured because of non available database system | The department to budget addidtional R50 000 for installation of the software because the current infrastructure is not compatable to the software. | 1 | The database was reviewed during the first quarter and no review was done during the second quarter. | Service provider(Predicate Solutions) was appointed to install a database software in May 2013. The service provider was handed to ICT for the implementation, up to now the software isnt installed due to poor/unavailble ICT resources. |  | Exception Found. Target was not achieved, Through enquiry with the Manager ICT it was indicated that the software is not compatible with servers of the municipality. She further indicated that it was discovered after the order was issued out that it was inaccurate and required a budget of R50 000 for the service provider to install a complete system | The department to budget addidtional R50 000 for installation of the software because the current infrastructure is not compatable to the software.
To conduct workshop on bidding processes with suppliers | Number of workshops held on bidding processes with suppliers. | 1 | 1 | OPEX | BTO | 1 | 0 | - | - | Not achieved | Workshop couldnt be done due to the workload that Unit had, as far as preparation of the AFS is concerned. Workshop was schedule for the 12th of December 2013 but couldn't take place due to the Memorial service for late State President to take place on the same week/day as memorial and was postponed to 21st January 2014 | The department to prioritise their work and work according to their annual work plan. | - | 0 | Workshop couldnt be done due to the workload that Unit had, as far as preparation of the AFS is concerned. Workshop was schedule for the 12th of December 2013 but couldn't take place due to the Memorial service for late State President to take place on the same week/day as memorial and was postponed to 21st January 2014 |  | Exception Found It came to our attention that workshop on bidding processes with suppliers couldn’t be done due to the workload that Unit had, as far as preparation of the AFS is concerned in the first quarter and in the second quarter it was schedulled for 12 December 2013 and the date was clashing with the memorial service day of State President. | The department to prioritise their work and work according to their annual work plan.
Disposal of obsolete assets. | Number of auctions held. | 2 | 2 | - | BTO | - | - | 1 | 0 | Not achieved | Bid to auction obsolete assets was advertised before the end of fourth quarter in preparation of disposal of assets in the 2nd quarter, however that couldn’t happen because no appointment could be made and as a result bids had to be re-advertised. Appointment of service provider for disposal of movable assets was only finalized in December 2013 | Service Provider to sign service level agreement with the legal unit before the 24 January 2013. | 0 | No assets were disposed during the second quarter. | Bid to auction obsolete assets was advertised before the end of fourth quarter in preparation of disposal of assets in the 2nd quarter, however that couldn’t happen because no appointment could be made and as a result bids had to be re-advertised. Appointment of service provider for disposal of movable assets was only finalized in December 2013 |  | Exception Found. Target was not achieved due to the delay in the appointment of service provider. The Actioneer was appointed on 30 December 2013 we further noted that the advert went out on the 17 September 2013 on Sowetan. | Service Provider to sign service level agreement with the legal unit before the 24 January 2013.

## CORPORATE SERVICES DEPARTMENT
2013/2014 QUARTERLY REPORTING TEMPLATE: CORPORATE SERVICES (SDBIP) PERFORMANCE INDICATORS AND TARGETS
strategy | Indicator | Baseline | Annual Target | Budget | Responsible Dept. | QUARTERLY PROJECTIONS | [7 empty] | Mid- Year target achieved or not | Explanation of variance | Expenditure (Ammount Spend) | Internal Audit verified or not | Mitigation
[6 empty] | 1ST QUARTER |  | 2nd QUARTER |  | 3rd QUARTER |  | 4th QUARTER
[6 empty] | Projections | Actual | Projections | Actual | Projections | Actual | Projections | Actual
KPA.1. INSTITUTIONAL TRANSFORMATION AND ORGANISATIONAL DEVELOPMENT
DEPARTMENT OF CORPORATE SERVICE
Recruitment and selection of competent staff. | Number of vacant position filled. | 225 | 20 | 1240372.51 | Corp | 5 | 6 | 5 | 4 | 5 | - | 5 | - | 10 | Ten positions filled during the first and second quarter. |  | Exception found Target was not met in the second quarter | None
Review of employment equity plan | One approved employment equity plan | 0 | 1 | - | Corp | - | - | 1 | 0 | - | - | - | - | 0 | Draft Equity Plan in place but waiting for inputs from the committee. |  | Exception found Target was not met. | Resuscitate the employment equity committee meetings.
| Number of officials trained | 157 | 80 | 57000 | Corp | 20 | 26 | 20 | 24 | 20 | - | 20 | - | 50 | 50 officials trained for first and second quarter |  | No Exception Found | None
| Number of councillors trained. | 89 | 57 | 57000 | Corp | 14 | 9 | 15 | 9 | 14 | - | 14 | - | 18 | Skiils audit forms for councillors indicate 3 year course instead of short courses |  | Exception found Target was not met in the second quarter. | More skills programme to be implemented in the 3rd and 4th Quarter and training to be provided to councillors on how to fill the skills audit forms.
Monitor and enforce compliance to OHS Act | Number of inspection visits of municipal buildings | 34 | 28 | - | Corp | 7 | 6 | 7 | 6 | 7 | - | 7 | - | 12 | 12 visits were conducted during the first and second quarter on the municipal offices. |  | Exception found Target was not met in both quarters. It was revealed that the target was suppose to be 6 not 7. | Technical service and other departments to inform HOS on time to do the inspection of their projects.
| Number of inspection visits of municipal construction projects | 71 | 40 | - | Corp | - | - | 10 | 0 | 20 | - | 10 | - | 0 | 2013/14 projects not yet site. |  | Exception found Target was not met due to late appointment of ervice providers. | Service Providers to be appointed in time.
| Number of OHS committee meetings held. | 4 | 4 | - | Corp | 1 | 1 | 1 | 1 | 1 | - | 1 | - | 2 | Two committee meetings were held. |  | No Exception Found | None
To achieve efficient labour relations management | Number of local labour forum meetings held. | 12 | 12 | - | Corp | 3 | 1 | 3 | 1 | 3 | - | 3 | - | 2 local labour forums meetings conducted | Meetings were postponed. Members did not form quorum. |  | Exception found Target was not met in both quarters due to postponment of other meeting caused by committee members not meeting the quorum. | Meetings to be scheduled in time to avoid postponments.
| Number of labour relation workshops held | 4 | 4 | OPEX | Corp | 1 | 1 | 1 | 1 | 1 | - | 1 | - | 2 | Two workshops were held during the first and second quarter. |  | No Exception Found | None
Provide legal services | Number of contracts vetted. | 12 | 15 | - | Corp | 4 | 0 | 4 | 0 | 4 | - | 3 | - | 0 | No procurement of new services that required SLA: Contract |  | Exception found Target was not met in the second quarter, only one contract was vetted no 0 as reported, due to delays in the appointment of service providers | None
[10 empty] | 1 | - | - | -
Develop fleet management strategy | Approved fleet management strategy | 1 | 1 | OPEX | Corp | - | - | 1 | 0 | - | - | - | - | 0 | Fleet Management strategy was submitted to Portfolio committee on 17 December 2013 for noting. |  | Exception found Target was not met, draft fleet management strategy was not taken to Council for approval. | Fleet management strategy to be presented to Council on the 24 January 2013
Provide effective and efficient fleet management | Number of fleet management reports compiled and submitted to management | 12 | 12 |  | Corp | 3 | 3 | 3 | 3 | 3 | - | 3 | - | 6 | six reports on fleet management were compiled. |  | No Exception Found | None
Transform the municipality from manual to paperless/e-municipality | Wireless technology network upgraded. | 1 | 1 | 500000 | Corp | - | - | 1 | 0 | - | - | - | - | 0 | Delay in the late appointment of the Network infrastructure project in the server room. |  | Exception found Target was not met due to late appointment of ervice provider. | Completion of the server room network infrastructure project.
| SCM database management system procured | 1 | 1 | OPEX | Corp | - | - | 1 | 0 | - | - | - | - | 0 | The order issued to the service provider caters only for the application and not the server. There is neither hardware nor budget for its procurement. |  | Exception found Target was not met due to communication breakdown between departments. | Finance department to budget extra R50 000 for installation of software.
| ICT steering committee established. | 1 | 1 | - | Corp | 1 | 1 | - | - | - | - | - | -- | 1 | Seven appointment letters for member to serve in the committee written and signed by the MM and distributed to the relevant recipients. |  | No Exception Found. | None
| SLA’s for customer care call centre and disaster recover switching centre developed. | 1 | 1 | - | Corp | - | - | 1 | 2 | - | - | - | - | 2 | Two SLA for the maintenance and support of the customer care call centre and Disaster recovery developed and signed. |  | Exception found Target was not achieved, the SLA is not yet signed as the service provider is still performing some test to give Municipality an assurance that they are capable to perform the work. Note: Call center SLA is included in the target of Disaster recovery switching Centre. | None
Develop service standard charter. | Number of service standards developed. | 1 | 1 | - | Corp | - | - | - | - | - | - | 1 | - | 2nd Quarter Target |  |  | Fourth Quarter Target | The Master Agreement for e-Venus is reviewed and awaits signature from Municipal Manager
Provide physical security for municipal property and officials | Number of monthly and ad hoc security management reports compiled. | 12 | 12 | OPEX | Corp | 3 | 3 | 3 | 3 | 3 | - | 3 | - | 6 | Three monthly reports were compiled for the quarter. |  | No Exception Found. | None
| Private security services procured | 1 | 1 | - | Corp | 1 | 1 | - | - | - | - | - | - | 1 | One security company appointed (Tyzer T Security). |  | Exception Found Target was met in the second quarter not first quarter. Appointment letter was signed on 30 December 2013 | Delays with regard to procurement processes
Provide coordination support to ward committees | Number of ward committee forums conducted. | 3 | 3 | OPEX | Corp | 1 | 1 | 1 | 1 | 1 | - | - | - | 2 | Two Ward Committee Forum meetings held during this quarter |  | Exception found Target was not achieved in the first quarter forum was postponed due to unavailability of the report. Two forums where held in the second quarter. | None
| Amount spent on ward committee support: monthly stipends | 0 | 261 | R3132,000 | Corp | R783,000 | 781 | 783 | 777 | R783,000 | - | R783,000 | - | 1555 | Target was not met due to positions not filled. | 1555 | Exception found Target was not achieved due to some of the positions for committee members not filled. Further we determined through inspection of the Budget report that the amount spend differs from the amount reported as follows: 1st Quarter = R284 320.00 | Ward committee posts to be filled.
| Number of Bi-monthly ward committee meetings held | 174 | 174 | - | Corp | 58 | 32 | 58 | 41 | 29 | - | 58 | - | 73 | Non adherence to meeting schedules and corum not formed |  | Exception found Target not met in the second quarter, It came to our attention that the target for the second quater was wrongly captured as 58 instead of 29. | Implementation of sunction for non attendance by Councillors.
Provide administrative support to council. | Number of Exco meetings held. | 12 | 12 | - | Corp | 3 | 3 | 3 | 4 | 3 | - | 3 | - | 7 | None |  | No Exception Found | None
| Number of Council meetings held. | 6 | 6 | - | Corp | 1 | 2 | 1 | 6 | 1 | - | 2 | - | 8 | Eight meetings were held |  | No Exception Found | None
| Number of portfolio committee meetings held | 96 | 96 | - | Corp | 24 | 16 | 24 | 3 | 24 | - | 24 | - | 19 | Nineteen meetings were held during the first and second quarter. |  | Exception found Meeting held in the first quarter is 14 not 16 as reported and 15 in the second quarter. It came to our attention that the cause for not achieving the target is non adherance to the schedule of meetings. | Non-adherence to scheduled meetings.
Provide Capacity and Coordination support to ward committees. | Number of municipal public accounts committee public hearing conducted | 1 | 1 | - | Corp | - | - | 1 | 1 | - | - | - | - | 1 | One municipal public hearing conducted. |  | Exception Found It came to our attention that the Public Hearing was never conducted during second quarter. | None
| Number of oversight reports submitted to council. | 4 | 4 | OPEX | Corp | 1 | 0 | 1 | 1 | 1 | - | 1 | - | 1 | Members of oversight reports were busy with their investigations and as a result they couldn’t site for first. |  | Exception Found We determined that the target was not achieved in the first quarter as MPAC was still in process of investigating the matters reffered to them by Council. | Internal Audit unit to send their reports to the committee timeously.

## MUNICIPAL MANAGER AND MAYOR'S
2013/2014 QUARTERLY REPORTING TEMPLATE: MUNICIPAL MANAGER AND MAYOR'S OFFICE (SDBIP) PERFORMANCE INDICATORS AND TARGETS
strategy | Indicator | Baseline | Annual Target | Budget | Responsible Dept. | QUARTERLY PROJECTIONS | [7 empty] | Actual achieved or not achieved | Explanation of variance | Expenditure (Amount spend) | Internal Audit verified or not | Mitigation
[6 empty] | 1ST QUARTER |  | 2nd QUARTER |  | 3rd QUARTER |  | 4th QUARTER
[6 empty] | Projections | Actual | Projections | Actual | Projections | Actual | Projections | Actual
Response to Audit queries | % of audit queries responder to within two days. | 100% | 100% | - | MMO | 100% | 100% | 100% | 100% |  |  |  |  | 100% | First and Second quarter All the queries raised by Auditor General and Internal Audit were responded to by Management. |  | No Exception found
Coordination reports from stakeholders | Number of stakeholders’ reports compiled. | 4 | 4 | - | MMO | 1 | 1 | 1 | 1 |  |  |  |  | 2 | Second quarter Presentation report on projects were submitted to Capricorn District Municipality on the 17 October 2013 to be presented on the Municipal Manager ‘s Forum held on the 22 October 2013. 13 November 2013 Mayor s Forum were held and on the 03 December 2013 Speaker s forum were held and attended. |  | Execption found. We could not verify the correctness and the accuracy of information reported in the first quarter as the supporting documents were not submitted for audit purpose.
Attend to client queries | Number of cases attended | 16 | 16 | - | MMO | 4 | 4 | 4 | 5 |  |  |  |  | 9 | Second quarter Five Cases of Illegal Occupants of RDP houses reported and still under investigation by COGHSTA |  | Exception found. We could not verify the correctness and accuracy of the information reported in the first quarter as the documents were not submitted for audit purpose. We verified that two cases were attended to not 5 as reported in the second quarter.
Monitoring and implementation of premiers hotline cases. | Number of premiers hotline progress reports compiled. | 4 | 4 | - | MMO | 1 | 1 | 1 | 1 |  |  |  |  | 2 | Second quarter 03 cases reported on the 06 Nov 2013 and Two cases resolve and One Case still under investigation |  | Exception found. We could not verify the correctness and accuracy of the information reported in the first quarter as the supporting documents were not submitted for audit purpose.
| Number of presidential hotline progress reports compiled | 4 | 4 | - | MMO | 1 | 1 | 1 | 1 |  |  |  |  | 2 | Second Quarter No cases reported and we are still Maintaining 100% |  | Exception found. We could not verify the correctness and accuracy of the information reported in the first quarter as the supporting documents were not submitted for audit purpose.
| Number of progress reports on implementation of council resolutions | 4 | 4 | - | MMO | 1 |  | 1 | 1 | [5 empty] | Second quarter Five Council were held Five Council were held Two Special Council Three Ordinary Council 22 Council Resolution were implemented 24 Council Resolution were noted 06 Council Resolution were pending 16 Council Resolution not implemented. We are still waiting response from the affected Departments Resolution not implemented. |  | Exception found. We could not verify the correctness and accuracy of the information reported in the first quarter as the supporting documents were not submitted for audit purpose. | Progress on implementation of Council resolution to be a standing item of the Executive Management meetings from third quarter.
Improve risk management system and protect the municipality from risks. | Risk management reports compiled. | 4 | 4 | - | MMO | 1 | 1 | 1 | 1 |  |  |  |  | 2 | First and Second quarter Risk Management reports were compiled in both quarters and presented to Risk Committee members during their meetings as follows: 12 September 2013 6 November 2013 |  | No Exception found
| Number of risk management meetings held. | 4 | 4 | 20 000.00 | MMO | 1 | 1 | 1 | 1 |  |  |  |  | 2 | First and Second Quarter Risk Committee meetings were held as follows: 12 September 2013 6 November 2013 |  | No Exception found
Implementation of 2013/14 internal audit plan | Number of internal audit reports submitted to audit committee | 4 | 4 | - | MMO | 1 | 1 | 1 | 0 |  |  |  |  | 1 | 4th quarter PMS Quarterly report for 2012/2013 financial year Cell – phone Allowance Financial position of the Municipality ICT Audit were presented to Audit Committee. Second quarter 4 Internal Audit Reports are completed, namely 1st quarter PMS report for 2013/2014 financial year, Risk Management report, Skills Development, Security Services. The reports were not presented to audit committee due to unavailability of the committee. |  | Not Applicable. We cannot audit ourselves | New Audit Committee members were interviewed in December 2013 and Council approved their appointment on 20 December 2013, they will be resuming their duties on 1 February 2014.
Implementation of internal audit charter | Number of awareness meetings conducted on audit | 2 | 2 | - | MMO | 1 | 1 | - | - |  |  |  |  | 1 | First Quarter Awareness campaign was held on 19 September 2013 for Technical Service Department. |  | Not Applicable. We cannot audit ourselves
Provide support to audit committee | Number of audit committee meetings conducted | 4 | 4 | 85 000.00 | MMO | 1 | 1 | 1 | 0 |  |  |  |  | 1 | First quarter Audit Committee Meeting was held on 30 August 2013. Second quarter Target was not achieved due to unavailability of Audit Committee. |  | Not Applicable. We cannot audit ourselves | New Audit Committee members were interviewed in December 2013 and Council approved their appointment on 20 December 2013, they will be resuming their duties on 1 February 2014.
| Number of audit committee quarterly reporting to council | 4 | 4 | 15 000.00 | MMO | 1 | 1 | 1 | 0 |  |  |  |  | 1 | First quarter Fourth Quarter Audit Committee Report was presented to Council. Second quarter Target was not achieved due to unavailability of Audit Committee Audit Committee members. |  | Not Applicable. We cannot audit ourselves | New Audit Committee members were interviewed in December 2013 and Council approved their appointment on 20 December 2013, they will be resuming their duties on 1 February 2014.
Provide support to external auditors. | Number of audit steering committee meetings conducted. | 8 | 8 | - | MMO | 1 | 3 | 7 | 7 |  |  |  |  | 10 | First Quarter Meetings held as follows: 5 August 2013 11 September 2013 17 September 2012 Second Quarter 9 October 2013 22 October 2013 16 October 2013 1 November 2013 6 November 2013 22 November 2013 25 November 2013 |  | Not Applicable. We cannot audit ourselves
Strengthen capacity on anti-corruption | Anti fraud and corruption prevention strategy reviewed. | 1 | 1 | - | MMO | 1 | 1 | 0 | 0 |  |  |  |  | 1 | Anti Fraud and corruption strategy was reviewed and approved by Audit Committee on 29 May 2013. |  | No Exception found
| Number of fraud prevention awareness meetings conducted | 4 | 4 | 103 300.00 | MMO | 0 | 0 | 1 | 0 |  |  |  |  | 0 | Target not achieved due to focus being diverted to preparation of the AFS. |  | Exception Found. It came to our attention that workshop on fraud prevention awareness could not be done due to focus being diverted to preparation of the AFS. | The Awareness meeting will be held during fourth quarter for all departments
Empowerment of special focus groupings. | Number of special focus structures and forums established and supported. | 2 | 2 | OPEX | MMO | 1 | 1 | 1 | 1 |  |  |  |  | 2 | First Quarter District youth council has appointed interim structure in August 2013 with constitutional mandate to perform duties. They are on the process of having official lunching. Second quarter On the 23rd October 2013 Special Focus Unit conducted the re-establishment meeting wherein all Community Based Organisitions were converged in Cultural Centre Hall to First Quarter District youth council has appointed interim structure in August 2013 with constitutional mandate to perform duties. They are on the process of having official lunching. Second quarter On the 23rd October 2013 Special Focus Unit conducted the re-establishment meeting wherein all Community Based Organisitions were converged in Cultural Centre Hall to re-aline Children Advisory Committee that serve in to the CBO Forum of the Municipality |  | No Exception found
| Number of special focus programme campaigns and awareness conducted. | 4 | 4 | OPEX | MMO | 1 | 1 | 1 | 2 |  |  |  |  | 3 | First Quarter Nelson Mandela Day Celebration was well attended wherein painting and fencing was done on the Makurung Multi-purpose Centre and 247 participants contributed on the success of the 67 minutes of their time on the 18th July 2013. Second Quarter On the 3rd December 2013, Special Focus Unit conducted awareness Campaign on HIV/AIDS and Gender Based Violence at Mamaolo Clinic. Lepelle Nkumpi and Childline Limpopo conducted Children ‘s Development Camp on the 29 November to 03 December 2013 at Happy Day Combined School in Westernburg wherein 60 Learners from various Schools located within the Municipality participated in the Camp and acquired educational services of Mentors from University of Limpopo | No Exception found
| Number of special group organisations linked to funding support. | 2 | 2 | - | MMO | 1 | 1 | 0 | 0 |  |  |  |  | 1 | First Quarter Itekeng Ntagane Crech received confirmation letter from National Lottery for funding to the amount of R518,850,00. | No Exception found
| Number of capacity bulding workshops conducted for special groups. | 2 | 2 | OPEX | MMO |  |  |  | 1 |  |  |  |  | 1 | Second quarter Career Development Workshop for People with Disabilities was conducted on the 21st November 2013 because this programme was earmarked by National Department of Women Children and People with Disabilities to form part of National Disability Month and we had to conduct earlier as it was scheduled for third Quarter |  | No Exception Found
| Number of special focus structures and forums (youth, gender, aged, children and people with disability and HIV/AIDS) supported. | 5 | 5 | OPEX | MMO | 1 | 0 | 2 | 3 |  |  |  |  | 3 | First Quarter Gender mainstreaming workshop was terminated on the third day of the training due to poor attendance by expected officials of the Municipality as this training was organized purely for Municipal officials, Councilors and members from various structures. Mayor’s Office and Gender Links have agreed on the continuation for the remaining days of the workshop which is scheduled to proceed during October 2013. Second Quarter Indigenous Game and fun Walk activities performed by Aged in all Clusters at Mahlatjane4 Hall on the 16 October 2013. The Unit further held CBO Forum meeting on the 3rd October 2013 at Cultural Centre Hall. Gender mainstreaming workshop was held on 11 November 2013 at Cultural Centres. |  | Exception Found. Target was not achieved in the first quarter as the workshop was postponed due to poor attendance by expected officials. | Gender mainstreaming workshop was rescheduled for second quarter.
Implementation of HIV/AIDS Plan | Number of HIV/AIDS forum meetings for lepelle-nkumpi AIDS council held. | 4 | 4 | - | MMO | 1 | 0 | 1 | 1 |  |  |  |  | 1 | First quarter Target was not achieves as the Local Aids Council meeting which was scheduled for 18 September 2013 due to the death of member. Second Quarter HIV /AIDS Technical Committee meeting was held on the 05 Nov 2013 to analyze Strategies on the Implementation of HIV/AIDS programmes and to pave a way forward for the Council meeting at Tribal Councils of the Municipality |  | Exception Found. we noted that meeting was postponed due to the death of one of Council members | Meeting was postponed for the second quarter
Coordination of special focus calendar activities | Number of special focus calendar |  | 10 | OPEX | MMO | 2 | 1 | 3 | 3 |  |  |  |  | 4 | First Quarter Special focus Unit managed to coordinate Women’s Day Celebration successfully wherein 8 buses was used to transport communities from all clusters of the Municipality on the 9th of August 2013. Lepelle-Nkumpi Women Charter For Positive. Values was not achieved because Gender vote was already exhausted by Women’s Day Celebration project. Second Quarter The Special Focus coordinated 16 Days of Activism of no Violence Against Women and Children Abuse organized by MEC Co orperative Governance, Human Settlement and Traditional Affairs in partnership with the Premier of Limpopo on the 22nd November 2013, 2. Special Focus Unit coordinated the International Day pf Persons with Disabilities held at Ga Maila Sekgololo( Killer Sports Ground) Makhuduthamaga Municipality on the 3rd December 2013. 3. Special Focus Unit coordinated Gender Based Violence Summit whereby Community members from various Structures participated in that Summit on 29th November 2013 at CDM. |  | Exception found. The target was not met in the first quarter, only one event was had due to finacial constrains. The vote was not adequately budgeted for. | Budget adequately for the activities in 2014/2015 financial year.
Strengthen Municipal Communication and public participation systems | Number of quarterly municipal newsletter editions released | 4 | 4 | 150 000.00 | MMO | 1 | 0 | 1 | 1 |  |  |  |  | 1 | First quarter Target was not achieved due to shortage of staff in the unit. Second Quarter News letter was realesed and distributed to officials and community members. |  | Exception found. Newsletter was not released in the first quarter. It came to our attention that it was due to the shortage of staff in the unit.
| Number of events management meeting s held | 2 | 2 | 350 000.00 | MMO | 1 | 2 | 1 | 12 |  |  |  |  | 14 | First quarte The following events were coordinated: 7 August 2013, Council meeting, 31 August Exco Lekgohla at Mafefe, Second quarter 14 October 2013 Imbizo with Department of Communication at Seleteng, 7 November 2013 Official Oppening of Landfill site, 19 November Official Handing Over of two houses in Mafefe, 21 November 2013 Awareness of person with disability and old age, 3 December 2013 HIV/Aids awareness campaign, 9 December 2013 Ward Committee forum meeting, 17 December 2013 Round table meeting with PMT, EXCO and Magoshi, 18 December Internal Sports Day year end, 6 November 2013 Council Meeting at Mafefe, 20 Novembet Council meeting Civic hall and 25 December Handing over of Christmas gift to new born children at Lebowakgomo Hospital. |  | Exception found. Through inspection of the supporting documents provided we verified that 11 events were attended to not 12 as reported.
Promote sports mass participation | Number of national, provincial and local games organized. | 2 | 2 | OPEX | MMO | 1 | 3 | 0 | 0 |  |  |  |  | 3 | First Quarter Municipal clusters participated on club Municipal clusters participated on club development competition with the Dept Of Sports arts And Culture between 7/09/2013, 21/09/2013 and 28/09/2013 at Nirvana, Seshego Stadium and Noordelike Laerskool Grounds. On 20th July 2013 Zebediela Progressive Athletic Club competed at Settlers Agricultural High School for Cross Country Athletics event, on 3 August 2013, they progressed to Limpopo Athletic Cross Country Provincial Championships event at Mahwelereng Stadium and on the 14th September 2013, the Club achieved to ASA National Cross Country Championships at Potchefstroom in North West Province. |  | Exception found. We could not verify the correctness and accuracy of the information reported in the first quarter as the supporting documents were not submitted for audit purpose.
| Number of indigenous festivals held. | 1 | 1 | OPEX | MMO | 0 | 1 | 1 | 0 |  |  |  |  | Target achieved in the first quarter | Indigenous games festival started on 3 August 2013 at cluster selections and they proceeded to the Provincial selection and we finally achieved where one player achieved to National and currently, the Municipality will be represented at international tournament. |  | No Exception found
| Number of arts and cultural activities hosted in all clusters | 4 | 4 | OPEX | MMO | 1 | 0 | 1 | 0 |  |  |  |  | 0 | There were no arts and cultural activities hosted in the clusters due to ineffective Art and Culture Council. |  | Exception found. It came to our attention that the target was not achieved due to ineffective Art and Culture Council. | Re - establishment of Art and Culture Council in the thrird quarter.

## TECHNICAL SERVICE DEAPRTMENT
2013/2014 QUARTERLY REPORTING TEMPLATE: TECHNICAL SERVICES (SDBIP) PERFORMANCE INDICATORS AND TARGETS
Strategy | Indicator | Baseline | Annual Target | Budget | Responsible Dept. | QUARTERLY PROJECTIONS | [7 empty] | Mid- year Target achieved or not | Explanation of variance | Expenditure (Amount Spend) | Internal Audit verified or not | Mitigation
[6 empty] | 1ST QUARTER |  | 2 nd QUARTER |  | 3rd QUARTER |  | 4th QUARTER
[6 empty] | Projections | Actual | Projections | Actual | Projections | Actual | Projections | Actual
KPA.2. BASIC SERVICES AND INFRASTRUCTURE DEVELOPEMNT
DEPARTMENT OF TECHNICAL SERVICES
Construction and maintenance of roads infrastructure. | Number of km of new municipal roads (gravel) constructed. | 0 | 0.5km | - | INFR | Maintenance of fleet. | Grader Machine services, Front loader awaiting parts to complete services, rest of machines received license discs | Consultation with Technical service portfolio committee | Grader Machine waiting procurement of tyres by Supply chain management unit and Front loader awaiting procurement of parts to complete services. Consultation with portfolio committe to be concluded third quarter | Construction of earth works | - | Completion of 0.5km road | - | Nil | Brake down of plant |  | Exception found In the first quarter it was reported that the fleet was maintained but we could not be provided with the evidance. We further noted that what is reported in the midyear differs with what was reported during first quarter. Target was also not achieved in the second quarter | Item to be submitted to portfolio committe for prioritisation of streets.
| Upgrading 7km road from gravel to block paving at zone F phase 2 | 3km | 4km | R11 354 850.00 | INFR | Advert for construction | Project is at Evaluation and Adjudication stage | Appointment of contractor | Project is at Adjudication stage | Construction of road | - | Completion of 4km road. | - | Nil | Delays in the apoointment of contractor. |  | Exception found Target not achieved in the second quarter. Through inspection of bid adjudication committee reports we verified that this project was not yet adjudicated in the 2nd quarter. We further noted that according to the procurement plan the project should have been adjudicated by 10/09/2013 | SCM to expedite appointment of contractors
| Upgrading from gravel to block paving of street and storm water in zone A (Rochville)/Tleane Phase 1: block paving, kerbs, installation and road marking/signage | 0 | 6.2km | R17 444 172.00 | INFR | Advert for construction | Project is at Evaluation and Adjudication stage | Appointment of contractor | Project is at Adjudication stage | Construction of earthworks | - | 6.2km block paving street and storm water. | - | Nil | Delays in the apoointment of contractor. |  | Exception found Target not achieved. Through inspection of bid adjudication committee reports we verified that this project was not yet adjudicated in the 2nd quarter. We further noted that according to the procurement plan the project should have been adjudicated by 10/09/2013. | SCM to expedite appointment of contractors
| Resealling and maintainance of tarred streets. | 0.8km | 4.5km | R5 000 000.00 | INFR | Scoping and planning | Tender document submitted to specification committee for comments and advertisement | Advert for contractor | Bid specification committe processes concluded and waiting for approval of tender advertisement bid specification committe processes concluded. | Appointment of contractor | - | Resealling of 4.5km. | - | Nil | Delays in convening Bid specification committe meetings. |  | Exception Found We verified that Specifications were forwarded to SCM on 22 November 2013 bid specification committee meeting was held on 19 December 2013 for approval. SCM Unit is waiting for Technical Services Unit to submit tender document before they can advertise the project. | SCM to expedite appointment of contractors
| Paving of Zone A and F market stall areas block paving, kerbs, installation and road marking | 0 | 7km | R700 000.00 | INFR | Scoping and planning | The process of registration on MIG MIS System is underway. | Advert for contractor | Bid specification committe processes concluded and waiting for approval of tender advertisement bid specification committe processes concluded. The project is in the process of registration on MIS for MIG funding. | Appointment of contractor | - | Construction of paving at zone A and F | - | Nil | Delays in convening Bid specification committe meetings. |  | Exception found We verified that the target was not achieved in the first quarter as Technical Services department was awaiting for LED Unit to make measurements. In the second quarter we determined that specification was forwarded to SCM Unit on 26 November 2013, bid specification committee held the meeting on 19 December 2013 to approve the specification. SCM Unit is waiting for Technical Services department to submit the Tender document before they can advertise the project. | SCM to expedite appointment of contractors
Number of environmentally sound storm water infrastructure. | Lining of storm water drainage in lebowakgomo zone B | 0 | 2.7km | 3999852 | INFR | Approval of designs | Project is at Evaluation and Adjudication stage and also the registration process is underway. | Advert for contractor | Project is at Adjudication stage | Appointment of contractor | - | 2.7km storm water drainage. | - | One Contractor appointed | The funding for the project is MIG Funds and the project in not yet registered on with MIG, still waiting feedback from MIG. |  | No Exception found. | SCM to expedite appointment of contractors
Improve access to electricity infrastructure | Number of new high masts installed. | 15 | 10 | R 600 000.00 | INFR | Identification crime areas | Two police stations have submitted the crime area and the other two are oustanding . | Advert for contractor | Four police stations have submitted the list and it has been presented to potfolio. It was discussed in potfolio meeting that Administration should compile list of all high mast consisting of non-functional and functional high mast within the municipality, as such the list will be proposed to portfolio with recommended villages without high mast lighting. Once the villages are identified the project has to be registered on MIS/Mig for MIG funds. | Appointment of contractor | - | Construction of high masts | - | Nil |  |  | Exception found Through perusal of the quarterly report we noted that consultation processes are ongoing. | Infrastructure to expedite priority list and register project with MIG to use MIG funds.
| High mast lighting | 0 | 15 | 2145150 | INFR | Identification crime areas | Two police stations have submitted the crime area and the other two are oustanding and also the process of registration on MIG MIS System is underway | Advert for contractor |  | Appointment of contractor | - | Construction of high masts | -
Improve access to electricity infrastructure | Number of households electrified at Morotse village. | 0 | 100 | R 302 000.00 | INFR | Upgrading from dual line to a three phase line. | Upgrading from dual line to a three phase line. | 100 households electrified. | 100 households connected but not energised , the VO for Upgrading from dual line to a three phase line has approved and work to commence in the third quarter. | - | - | - | - | Nil |  |  | Exception Found. Alrhough 100 house holds were electrified in the first quarter the target was not achieved, challange was the dual line which need to be upgraded, we determined that the Acting MM approved the variation for the upgrading of the Dual line on 9 December 2013 | The contractor to speed up construction of the line to allow switch on by ESKOM to be effecetd.
| Number of households electrified at Mehlareng (50), Dublin (50), Ngwaname (30), Matome (120) and Bolatjane (60) villages. | 0 | 310 | R3 465 675.00 | INFR | Approval of designs | Advertised for contractor | Advert for contractors. | Project is at Adjudication stage | Appointment of contractors | - | 310 households electrified. | - | project advertised |  |  | Exception found. Municipality was waiting for Eskom to approve designs in the first quarter. Second Quarter 1. We determined that Mehlareng was advertised for 115 households while budgeted for 50 households. 2. We verified through consultation with SCM Unit and inspection of the adverts that the following projects were not advertised: Dublin (50) Ngwaname (30) Matome (120) Bolatjane (60) The total amount budgeted for Mehlareng(50), Dublin (50), Ngwaname (30), Matome (120) and Bolatjane (60) for 3 465 675.00. | SCM to expedite appointment of contractors
| Number of households electrified at Serobaneng (41),Hweleshaneng (65), Mogodi (40) and Makgoba (120) villages. | 0 | 266 | R3 059 000.00 | INFR | Approval of designs | Advertised for contractors | Advert for contractors. | Project is at Adjudication stage | Appointment of contractors | - | 266 households electrified. | - | Project advertised |  |  | Exception found. Municipality was waiting for Eskom to approve designs in the first quarter. Second Quarter Through inspection of the IDP and Budget for 2013/2014 financial year we verified that the number of households are 41 for Serobaneng, 65 for Hweleshaneng, 40 Mogodi and 120 for Makgoba while the Bid documents state the number of households as 131 Serobaneng, 48 for Hweleshaneng, 58 Mogodi and 122 for Makgoba | SCM to expedite appointment of contractors
| Number of households electrified at Maijane (30) and Leshoaneng (350) | 0 | 380 | R735 850.00 | INFR | Approval of designs | Advertised for contractors | Advert for contractors. | Project is at Adjudication stage | Appointment of contractors | - | 380 households electrified. | - | Target Achieved |  |  | Exception found. Municipality was waiting for Eskom to approve designs in the first quarter. Second Quarter Through inspection of the IDP and Budget for 2013/2014 financial year we verified that the number of households are 30 for Maijane and 350 for Leshoaneng while the evaluation report state the number of households as 90 for Maijane and 194 for Leshoaneng. We further determined the budgeted amount as R735 850.00 while the budget reflect R3 465 675.00. | SCM to expedite appointment of contractors
| Number of households electrified at Staanplaas village. | 0 | 120 | R178 160.00 | INFR | 120 households energized | Advertised for contractors |  | Eskom has submitted a report to LEDET regarding the Marula trees cut by community on the feeder line route and LEDET has not responded on the wayforward to ESKOM. | - | - | - | - | Target not Achieved |  |  | Exception found. Municipality was waiting for Eskom to approve designs in the first quarter. Second quarter It came to our attention that the target was not achieved as they are still waiting for the response from Eskom and LEDET regarding the cutting of Marula tree. | SCM to expedite appointment of contractors
| Number of households electrified at Mphaganeng village. | 0 | 12 | R115 000.00 | INFR | Approval of designs | Advertised for contractors | Advert for contractors. | Project is at Adjudication stage | Appointment of contractors | - | 12 households electrified. | - | project advertised |  |  | Exception found. Municipality was waiting for Eskom to approve designs in the first quarter. Second Quarter 1. We verified through inspection of the list of projects to be implemented by Eskom that Mphaganeng Village reflect on the list. 2. We further determined that Electrification of Motantanya (318 households) which is budgeted for R5000 000.00, funded by DME was advertised and evaluated on 19 – 23 December 2013 but the project does not reflect on the SDBIP and the IDP FOR 2013/2014 financial year. | SCM to expedite appointment of contractors
| Number of households electrified at Lebowakgomo zone F | 0 | 500 | R1 430 000.00 | INFR | 500 households energized | Completed | - |  | - | - | - | - | project completed |  |  | No Exception found.
| Number of households electrified at Klienhauiwel village. | 0 | 285 | R3 277 500.00 | INFR | Approval of designs | Project to be implemented by ESKOM | Advert for contractors. | Project to be implemented by ESKOM | Appointment of contractors | - | 285 households electrified. | - | project advertised |  |  | Exception Found. Through perusal of council resolution we noted that Council resolved to relocate funds of this project to complete electrification of Madisha Leolo and Magatle it was further indicated that the project will now be implemented by Eskom.
Development of community and social infrastructure | Community Hall build at Dublin: construction of the building with flooring, roof, mansory, painting, fence, electricity, septic tank and water supply | 0 | 1 | R 3 750 000.00 | INFR | Resolve Permission to occupy. | The position of the site is not yet finalised. | Site establishment. | The position of the site is not yet finalised. | Construction | - | One community hall constructed. | - | Nil |  |  | Exception Found. It came to our attention in the first and second quarter that project could not commence as there is no consensus of location of the hall. | Resolve Permission to occupy through the councillor and office of the Mayor .
| Construction of Rafiri community hall : construction of the building with flooring, roof, mansory, painting, fence, electricity, septic tank and water supply | 0 | 1 | R2 500 000.00 | INFR | One Construction of a Hall | Practically complete and wainting for installation of Spetic tank and electricity connection. | - | Practically complete and wainting electricity connection. | - | - | - | - | Nil | waiting for connection by Eskom |  | Exception found. Target was not achieved in the first quarter as follows: Through physical inspection conducted on 14 November 2013 we verified that the hall is not completed. The following has not yet been constructed: 1. Sceptic tank 2. Water supply | Make follow up with Eskom regarding electrical connection.
| Construction of Ga Seloanecommunity hall : construction of the building with flooring, roof, mansory, painting, fence, electricity, septic tank and water supply | 0 | 1 | R300 000.00 | INFR | One Construction of a Hall | Practically complete and wainting for electricity connection. | - | Practically complete and wainting for electricity connection. | - | - | - | - | Nil | waiting for connection by Eskom |  | Exception Found. Through physical inspection conducted on 14 November 2013 we verified that the hall is complete. The contractor is awaiting electrification of the hall by Eskom. It was indicated that the contractor submitted a request for electrification to ESKOM | Make follow up with Eskom regarding electrical connection.
| Construction of Mogoto community hall: construction of the building with flooring, roof, mansory, painting, fence, electricity, septic tank and water supply | 0 | 1 | R2 000 000.00 | INFR | One Construction of a Hall | Practically complete and waiting for electricity connectio. | - | Practically complete and waiting for electricity connection. | - | - | - | - | Nil | waiting for connection by Eskom |  | Exception found. Through physical inspection conducted on 14 November 2013 we verified that the hall is complete. The contractor is awaiting electrification of the hall by Eskom. It was indicated that the contractor submitted a request for electrification to ESKOM | Make follow up with Eskom regarding electrical connection.
| Refurbishment of Mamaolo Hall. | 0 | 1 | R100 000.00 | INFR | One community Hall refurbished | Project is at Evaluation and Adjudication stage | - | Project is at Adjudication stage | - | - | - |  | Nil | waiting for appointment of service provider |  | Exception found We determined that the tender was advertised on 19 September 2013, It came to our attention that errors on the specification was identified after the tender was advertised, management resolved to readvertise the tender. SCM Unit still awaiting for the correct specification from Technical Services Department to date (January 2014) | SCM to expedite appointment of contractors
| Development of new cemetery at lebowakgomo | 0 | 1 | R3 680 000.00 | INFR | Advert for contractor and appointment |  | Construction | The transfer of land for development of cemetery is not yet complete and the consultant could not finalise the designs and tender document. | One new cemetery completed | - | - | - | Nil | The transfer of land for development of cemetery not yet completed |  | Exception Found target was not archived due to initial identified land not being suitable as a rock was encountered there was delays in re-identification of new area’s to explore for possible location of cemetery. We also noted that newly identified area belongs to Public works and process is in place to request permission to use the land. | Meeting to be arranged with the MEC Public Works to expedite transfer of Land for development of cemetery.
| Extension of Municipal office | 0 | 1 | R6 000 000.00 | INFR | Completion of building |  | - | 80% Complete | - | - | - | - | Nil | Non Payment to contractor due to lack of infomation on the project and this caused delays in completing the project. |  | Exception Found. Through physical verification conducted on 15 November 2013 we noted that roofing is in progress and the project was supposed to be completed in the 4th quarter of 2012/2013 financial year. We further noted in January 20th that there are no people on site. It came to our attention that there are disputes relating to the payment of the contractor due to the changes in the scope of work. | The contractor to submit new programme of works and to be monitored through the new programme.
| Refurbishment of Noko Tlou stadium | 0 | 1 | R300 000.00 | INFR | Completion of refurbishment of Noko Tlou. | - | - | Scope of works as in the BOQ has been completed But the facility is not functional due to vandalism. | - | - | - | - | Nil | There was vandalism on the building due to the delay on the appointment of the contractor |  | Exception Found First Quarter Through physical verification of the project on 15 November 2013 we noted the project is not completed. The following were not yet constructed as per the approved scope: • Electricity • Sanitary Facilities • Kitchen Zink • Ceiling • Trap door • 20m flat wrap razor wire was in progress during the visit. Second Quarter It came to our attention that there is no progress on what was outstanding in the first quarter as the stadium was vandalized and they are still in process of appointing the services provider Risimat was appointed for R291 049.18 and the amount of R132 562.11 was paid for the work performed. There are some of the work not done as per scope of work as reported in the first quarter. | A new scope of work to be compiled to accomodate the items vandalised for the project to be completed.
| Revitalization of municipal building at civic centre : Stage, lighting, flooring, interior design and mansory | 0 | 1 | R4 325 221.00 | INFR | Approval of designs | Project is at Evaluation and Adjudication stage | Advert for contractor | Contractor appointed | Appointment of contractor | - | Revitalization of municipal building at civic centre. | - | Target Achieved | None |  | No Exception found. | None
| Refurbishment of Cultural Centre: Stage, lighting, flooring, interior design and mansory | 0 | 1 | R2 880 000.00 | INFR | Approval of designs | Project is at Evaluation and Adjudication stage | Advert for contractor | The project scope has been compiled for Tender advertisement. | Appointment of contractor | - | Revitalization of municipal building at cultural centre. | - | Nil | Delay in the compilation of Bid Specification to Bid Specification committe. |  | Exception Found. Through inspection of the quarterly report we noted that the project was not advertised due to delay in compilation of bid specification. In terms of the procurement plan this project should have been adjudicated by 10/09/2013 | Infrastructure to expedite compilation of tender document for advertisement and appointment of contractor.
| Refurbishment of Lebowakgomo sports complex | 0 | 1 | R6 113 678.00 | INFR | Approval of designs | Project is at Adjudication stage and also the registration process is underway. | Advert for contractor | Project is at Adjudication stage and also the registration process is underway. | Appointment of contractor | - | Revitalization of Lebowakgomo sports complex | - | Nil | The funding for the project is MIG Funds and the project is not yet registered on with MIG, still waiting feedback from MIG. |  | Exception found. Through inspection of bid adjudication committee we noted that the project was referred back to bid evaluation committee because the committee disqualified bidders with 5GB whereas the municipality required 5CE or higher. In terms of the procurement plan this project should have been adjudicated by 10/09/2013. | SCM to expedite appointment of contractors
| Development of Residential sites at unit H | 0 | 1 | R12 532 400.00 | INFR | Advert for construction | Design stage | Appointment of contractor | Design complete and there is no ROD/authorisation on EIA from LEDET on the project. | Development of residential sites at unit H | - | - | - | Nil | Delays in the specialised study |  | Exception Found In the first quater target was not achieved due to land disputes . Second Quarter It came to our attention that municipality is waiting for completion and approval of environmental Impact Assessment by LEDET | SCM to expedite appointment of contractors
| Construction of a 900m palisade fencing at Ga Ledwaba | 0 | 1 | 1000000 | INFR | Advert for construction | Project is at Evaluation and Adjudication stage and also the registration process is underway. | Appointment of contractor | Contractor appointed | Construction | - | Completion of palisade fencing. | - | Target Achieved | None |  | No Exception found. | None
Enforcement of building regulation and standards | Number of building inspections conducted | 660 | 60 | - | INFR | 15 | 49 | 15 | 27 | 15 | - | 15 | - | 76 | None |  | Exception found First Quarter Through inspection of the supporting documents we verified that 31 building inspection were conducted and not 49 as reported Second Quarter We could not verify the correctness and accuracy of the information reported in the first quarter as the documents were not submitted for audit purpose. | None
Enforcement of building regulation and standards | Number of housing plans approved. | 180 | 40 | - | INFR | 10 | 5 | 10 | 25 | 10 | - | 10 | - | 30 | None |  | Exception Found. First Quarter We could not verify the correctness and accuracy of the information reported in the first quarter as the documents were not submitted for audit purpose. Second Quarter Through inspection of the Plans submission register up to November 2013 we verified that 47 plans were submitted, through inspection of the reconciliations from Finance department we determined that the payments for approval of plans that reflect on the above register are for 8 not 25 plans as reported. | None

## PLED
2013/2014 QUARTERLY REPORTING TEMPLATE: PLED (SDBIP) PERFORMANCE INDICATORS AND TARGETS
Strategy | Indicator | Baseline | Annual Target | Budget | Responsible Dept. | QUARTERLY PROJECTIONS | [7 empty] | Mid- year Target achieved or not | Explanation of variance | Expenditure (Amount Spend) | Internal Audit verified or not | Mitigation
[6 empty] | 1ST QUARTER |  | 2 nd QUARTER |  | 3rd QUARTER |  | 4th QUARTER
[6 empty] | Projections | Actual | Projections | Actual | Projections | Actual | Projections | Actual
Annual Review of IDP | No. of IDP technical committee meeting held. | 0 | 4 | Opex | PLED | 1 | 0 | 1 | 0 |  |  |  |  | Nil | Technical committee not yet constituted. |  | Exception Found It came to our attention in both quarters that the committee has never convened a meeting due to non attendance by member | Notices to be issued in time through ward committee members and councillors
| No. of IDP steering committee meetings held. | 4 | 4 | Opex | PLED | 1 | 0 | 1 | 0 |  |  |  |  | Nil | Efforts to arrange meeting through Acting Municipal Manager's Office could not succeed. |  | Exception Found It came to our attention that target was not archived due to efforts to arrange meeting through Acting Municipal Manager’s Office being unsuccessful. | Notices to be issued in time through ward committee members and councillors
| No. of departmental strategic planning sessions held. | 6 | 6 | Opex | PLED |  |  | 6 | 6 |  |  |  |  | 6 | None |  | Exception Found. Target not achieved, we determined that Institutional Strategic planning ws held from 8 to 10 January 2013 not departmental. , it was confirmed that the departmental Strategic Planning had to be postponed due to the funeral of the late former president Nelson Mandela. | None
| Number of ward based consultations conducted. | 29 | 29 | Opex | PLED |  |  | 29 | 29 |  |  |  |  | 29 | None |  | No Exception Found. | None
To monitor and evaluate organizational performance | 2013/14 SDBIP approved by the Mayor | 1 | 1 | Opex | PLED | 1 | 1 | [6 empty] | 1 | None |  | No Exception Found. | None
| Number of quarterly reports tabled to Council | 4 | 4 | Opex | PLED | 1 | 1 | 1 | 1 |  |  |  |  | 2 | None |  | Exception Found. We inspected council resolutions for the month of October to December 2013 and there was no evidence to proof that quarterly reports were submitted to council in the second quarter. | None
| Annual Performance report tabled to Council | 1 | 1 | Opex | PLED | 0 | 0 | 1 | 1 |  |  |  |  | 1 | None |  | Exception Found. We inspected council resolutions for the month of October to December 2013 and there was no evidence to proof that annual performance reports was submitted to council. | None
Number of individual performance agreements signed by Senior Managers | 6 | 6 | 6 | Opex | PLED | 6 | 3 | 0 | 1 |  |  |  |  | 4 | Executive Manager: Technical services assumed her duties on the 15th January 2014 and the Municipal Manager still on suspension. |  | Exception Found. We inspected Individual performance agreement of the Executive Manager Planninng and LED Who commenced his duties on 1 December 2013 as per agreemen, We verified that the performance agreement was signed by the Executive Manager on 8 January 2014 and the Acting Municipal Manager on 9 January 2014. Although the signing of the contract was within 90 days as prescribe by the Act, the target was not met during second quarter as reported that one target was achieved. | Council to finalise the suspension to avoid delays in the signing.
Number of individual performance assessments conducted for Senior Manager | 12 | 24 | 6 | Opex | PLED | 6 | 0 | 6 | 0 |  |  |  |  | 0 | Assessments were postponed due to unavailability of the the audit report from the internal audit unit |  | Exception Found In the first quarter we were informed that the individual performances where not conducted due to due to two Senior Manager positions being vacant and suspension of the Municipal Manager. Second Quarter It came to our attention that the assessments were postponed as the committee members requested the audited reports before they can proceed with the assessments. | Internal audit unit to conduct their audit before the assessments
Provision of information to SMME’s to capacitate them on procurement processes. | Number of capacity building workshops conducted on bidding process | 2 | 4 | Opex | PLED | 1 | 3 | 1 | 1 |  |  |  |  | 4 | None |  | No Exception Found. | None
Support and assist informal traders to formalize their business. | Number of seminars conducted on business registrations | 2 | 4 | Opex | PLED | 1 | 1 | 1 | 1 |  |  |  |  | 1 | None |  | No Exception Found. | None
Place marketing and tourism attraction | Number of municipal shows held. | 0 | 1 | Opex | PLED | 1 | 1 | 0 | 0 |  |  |  |  | 1 | None |  | Exception Found. We could not verify the correctness and accuracy of the information reported in the first quarter as the supporting documents were not submitted for audit purpose. | None
Create community empowerment opportunities. | Number of road shows held with informal trading. | 0 | 4 | Opex | PLED | 1 | 1 | 1 | 1 |  |  |  |  | 1 | None |  | Exception Found. We could not verify the correctness and accuracy of the information reported in the first quarter as the supporting documents were not submitted for audit purpose. | None
Provide technical support to cooperatives. | Number of cooperatives linked to financial and technical assistance | 4 | 4 | Opex | PLED | 0 | 0 | 2 | 2 |  |  |  |  | 2 | None |  | Exception found. We verified that GM Leather Tannery was linked Zion Christian Church for supply of shoes to the church on 29 November 2013 We could not be provided with the supporting documents to substantiate that the other cooperative that was linked to financial and technical assistance. | None
| Number of monitoring and sites visits undertaken. | 10 | 12 | Opex | PLED | 3 | 4 | 3 | 3 |  |  |  |  | 7 | None |  | Exception found. Second Quarter We verified through inspection of the out of office form and Project consultation form to verify that Hlakano Youth Bakery was visited on 13 December 2013. We could not be provided with the supporting documents to substantiate for two other visited for monitoting. | None
Development of residential areas in Lebowakgomo | Number of sites disposed in Lebowakgomo unit H | 0 | 293 | Opex | PLED | 0 | 0 | 293 | 0 |  |  |  |  | 0 | ROD has not been issued by the department of economic development, environment and tourism but designs for reticulations have been completed |  | Exception found. Through enquiry with the Town Planner on 16 January 2014, we found that disposal of sites has not yet started, however an application for environmental authorisation for restoration of sites at lebowakgomo Unit H was made. | Assist the service provider to facilitate the issuing of ROD by the department of economic development and tourism.
To support traditional authorities on subdivision and allocation of stands. | Number of workshops held with traditional leaders regarding land issues. | 2 | 2 | Opex | PLED | 0 | 0 | 1 | 1 |  |  |  |  | 1 | None |  | No Exception Found. | None