## Community Services
COMMUNITY SERVICES DEPARTMENT
1ST QUARTER REPORT (JULY-SEPTEMBER 2011)
Strategy | Indicator | Baseline | Annual target | Budget | 1st Qtr September 2011 |  | 2nd Qtr December 2011 |  | 3rd Qtr March 2012 |  | 4th Qtr June 2012 |  | Explanation of Varience
[5 empty] | Proj. | Act. | Proj. | Act. | Proj. | Act. | Proj. | Act.
Provide sustainable Waste Management Programmes | No. of new Households provided with waste collection services at Mamaolo, Seleteng,Mashite | 0 | 7000 | R5 400 000 CDM | Meeting with affected councillors | Two meetings held with the affected Councillors
CDM
| Develop waste management standards | 0 | Waste management standards developed | Opex | Information gathering process | Draft copy available
| Closure and rehabilitation of Lebowakgomo dumping site | illegal dumping site | 1 | Opex | [8 empty] | 4th quarter target
| No. of transfer station licensed at Moletlane, Seleteng and Lebowakgomo Zones A & F | 0 | 4 | Opex | Identication of sites | Letters written to affected Tribal Authorities.
| Facilitate the developmenr and management of waste disposal site at Lenting | 0 | 1 | 16 000 000 CDM |  | Site handover done on the 19th of September. Site clearance commenced and site camp erected
Render support to recycling initiative | No. of Multy-Buy Bag Centre in Lebowakgomo Zone A | 0 | 1 | R2 000 000 Buyisa-e-Bag | Acquire waste management license | Application submitted to the Dept of Economic Dev, Env & Tourism | [7 empty] | 4th quarter target. Awaiting waste managmenet license
| No. of recyclers workshopped | 0 | 50 | Opex | Arrange a worksop for 50 recyclers | Recycling workshop held on the 25th of August , ±47 people attended | [6 empty] | Cleaning camapign was not done due to poor turnout of volunteering | The cleaning campaing could not be done on the 26th of August due to poor turn over of volunteers
Biodiversity conservation and management | No. of wetlands supported: Mohlapetsi | 1 | Mohlapetsi wetland supported | R20 000 Opex |  | A meeting was held from the 15-16 September to discuss the management plan of the wetland at the University of Limpopo and the following day the wetland was visited by the managment committee
| No. of wetlands profiled: Motlapodi | 1 | Motlapodi wetland profiled | R20 000 Opex | [8 empty] | 4th quarter target
Provide free basic services | No. of indigents registered | 15000 | 20000 | 20000 | Capturing of information | ±3 500 forms received.only 1 793 had complete information | Indigent register available | [5 empty] | most of the forms not back and the ones received are incorrectly filled and had no supporting documents such as Ids and payslips
Coordination of disaster managment | No. of disaster management plan developed | 0 | 1 disaster managment plan | 22282 | Conduct risk assessment | Risk assessment conducted in 10 wards. CDM advertised a tender for the development of disaster management plans for all the local municipalities
Public Road Safety | Scholar patrols established in Rusplaas and Mogoto Primary Schools | 0 | 2 | Opex | Collection of equipment from the Department of Roads and Transport | Equipment delivered from the Dept of Transport | [6 empty] | 4th quarter target
| Accident Bureau Centre established | 0 | 1 | Opex | Benchmarking at Stations where the Unit has been established | Traffic division together with the Executive Manager attended the Benchmarking tour at Ekhurhuleni Metro
Compliance to Testing Standards and Prescribed Legislations | No. of reports generated to respond to National or Provincial inspections within 30 days | 4 | 4 | Opex | 1 | 2 visits were conducted by the Provincial Department and 1 visit from the National Department. A report was generated responding to the queries raised
Upgrade of Testing Centre from Grade B to A | Motor Cycle Track Constructed | 0 | Grade A testing facility | opex |  | A briefing meeting was held with Infrastructure Department to do the specification | [6 empty] | 3rd quarter target
| Upgraded vehicle Testing Centre | Grade B VTS | Grade A testing facility | Department of Transport | [8 empty] | 4th quarter target
Improvement of testing facilities | Alley docking of light motor vehicle relocated | DLTC | Separated light and heavy motor vehicle testing centre | opex |  | A briefing meeting was held with Infrastructure Department to do the specification | [6 empty] | 3rd quarter target
Extension of licensing services | No. of new satellite offices for the renewal of Licensing discs established at Zebediela | 0 | Satellite office of rebewal of license discs establihed | opex | Identification and acquisition of site | A letter requesting space was sent to Mokopane SAPS
Provide sustainable Waste Management Programmes | No. of Existing households and businesses provided with waste collection services in Lebowakgomo | 9942 | 9942 | 300000 | Ongoing | waste collection done as per the weekly roaster | Ongoing | [5 empty] | waste collection was not done for two weeks during August due to municipal industrial action
| No. of Existing households provided with waste collection services in Mathibela,Rakgoatha, Matome and Makweng (Food for Waste) | 4500 | 4500 | 1200000 | Ongoing | waste collection done as per the weekly roaster | Ongoing | [5 empty] | waste collection was not done for two weeks during August due to municipal industrial action and delay in the delivery of food parcels to beneficiaries
Establishment of park in the CBD | No. of parks developed in the CBD | 1 | 1 | R3 200 000 DEA | Site hand over to Contractor | DEA introduced the contractor around July. A visit to parks in Johannesburg was done by the Waste Managment Officer and the Town plan as a benchmark. Contractor busy with designs
Coordination of Disaster Management | No. of disaster incidents attended to within 3 hours | 150 | As per occurrence | 22282 | As per occurrence | 8 Fire incidents attended to, 4 child-headed families visited and 1 indigent household provided with food parcels during a death case. Preparatory meetings held at CDM on Wednesdays for the preparation of World reduction day to be held at Ga-Seloane on the 5th of October. A letter was sent to the Dept of Education to assist Serobaneng Primary School by building two blocks of classroom to compensate for the damaged school builing due to the disaste that occured around 2002
Public Road Safety | No.of traffic law enforcement roadblocks conducted | 50 | 60 | Opex | 15 | 16
| No. of auctions of impounded goods held | 10 | 4 |  | 1 | 2
Enforcement of municipal by-laws | No.of operations conducted | 12 | 12 | 10000 | 3 | 3
Registration and licensing of vehicles | Number of vehicles registered | 1200 | 1200 | Opex | 300 | 479
| Number of vehicles licensed | 8400 | 8400 |  | 2100 | 2338
Quality testing of PrDP, driving licences and vehicles | No. of driving licences tested | 3360 | 4400 |  | 1100 | 755 | [6 empty] | The industrial action affected the testing of driving license that were scheduled to take place during August
| No. of learners licences tested | 2880 | 1400 |  | 360 | 551
| No. of Professional Driving Permits issued | 840 | 840 |  | 210 | 210
| No. of vehicles tested | 144 | 200 | [9 empty] | VTS pit under repair
| No. of sensitive applications submitted to Law Admin and Help Desk | 158 | As per occurrence |  | As per occurrence | 70
Promotion of Sports and Recreational Activities | No. of sporting activities held | 9 | 12 | Opex | 3 | 1. Athletic O.R Thambo games.2. Indigenous festivals from ward, cluster, Municipal to the District level. 3. Attended three Cross Country Marathon 4. Launched women football tournament.
| No. of new sporting codes launched |  | 1 | [9 empty] | 2nd quarter target
|  | 1 | 1
| No. of identified sports federations launched | 9 | 2 | [9 empty] | 3rd and 4th quarter
| No. of capacity and awareness campaigns held in all clusters | 4 | 5 |  | 5 | Held indigenous games awareness campaign at Mafefe, Zebediela, Mathabatha and Mphahlele clusters.
| No. of Indigenous games held | 1 | 1 |  |  | 1 programme on indegenous games was held | [6 empty] | 3rd quarter target
| OR Tambo games | 1 | 1
| No. of OR Tambo games held | 1 | 1 |  |  | Selection on 11 codes was done from ward to provincial level | [6 empty] | 3rd quarter target
| No. of Mayor’s ball games tournaments held | 1 | 1 | [9 empty] | 3rd quarter target
Sport mass participation | No of sporting codes supported | 7 | 7 |  | 1 | Kgagatlou Secondary School provided with rugby equipment
| No. of Satellite sports hubs re-Established | 3 | 3 |  |  | Hub coordinators were appointed for Mafefe, Mphahlele and Zebediela Clusters | [6 empty] | 3rd quarter target
| No. of Mayor’s marathon held | 1 | 1 |  | 1 | The Mayor's marathon was postponed | [6 empty] | The date set clashed with the provincial heritage day celebration. To be held during October 2011
Arts and Cultural activities | No. of arts and cultural activities hosted | 4 | 4 |  | Opening of exhibitions center and celebration of heritage day | Local I can sing auditions held on the 16th of September 2011 and 15 artists represented LNM at District level on the 17th of September at University of Limpopo. The Provincial auditions were held on the 29th of September at Polokwane Royal hotel and there was no artist from LNM. The CD for the previous winners were launched on the day. Celebrated Nelson Mandela Day celebration at Phalakoane drop-in centre (painted the centre and provided them with groceries) | [6 empty] | local celebration of heritage day and the opening of the arts centre postponed due to the provincial heritage day to be held at Ga-Mphahlele
| No. of registered and protected heritage sites and resources | 1 | 2 | [9 empty] | 2nd quarter target
Provision of Library Services | No. of functional Modular Library established at Seleteng | 0 | 1 | Opex | Conduct needs analysis and submit to Dept of Sport, Arts and Culture | Needs analysis conducted with the Dept of Sport,Arts & Culture | [6 empty] | 4th quarter target
Environmental cleaning and greening | No. of cleaning programmes implemented | 7 | 4 |  | 1 | Cleaning was not done | [6 empty] | Cleaning campaign failed due to poor attendance which led to cancellation
| No. of trees planted ( greening) | 200 | 1000 |  | 250 | 270 Trees were planted at Malemang village and Traffic Station. The Department of Forestry donated 100 fruit trees which were planted at RDP houses in Malemang. Obtained position 2 during the Greenest Municipality Competion in the District (received an award and R15 000)
| No. of illegal dumps cleared | 27 | Ongoing |  | Ongoing | no progress registered | [6 empty] | Machinery breakdown hampered the progress
| No. of job opportunities created through EPWP | 269 | 300 | R270 000 | 140 | 40 temporary workers employed for litter picking, de-bushing and street cleansing. 4 data captures were appointed for the capturing of information in the indigent register | 100 |  |  |  | 60
FINANCIAL AND ADMINISTRATIVE CAPABILITY
Revenue collection | Amount collected from traffic fines | 270000 | R640 000 |  | R160,000 | 117780 |  |  |  |  | 160 000 |  | The industrial action affected the payment of fines. People fail to pay until issued warrants of arrests
| Amount collected from cattle pound | 250000 | R400 000 |  | R100,000 | 58089.95 | [6 empty] | The animals are collected by owners immediately after impoundment and only pay admin fee
| Amount collected from licensing | R6 428 973.31 | R6 500 000 |  | R1 625 000 | Total= R1 576 166.90 100% for the municipality=R787 802.75 | [6 empty] | Industrial action affected revenue collection
| Amount collected from public facilities | 117025 | R130 000 |  | 32500 | 23149 | [6 empty] | Civic hall and stadium still under construction